## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Login | Authentication | Admin, Parent, Driver | Allows a registered user to sign in with email and password; on success the system redirects to the role-specific dashboard. | Trần Quốc Huy | Done | iter1 | none
2 | Register | Authentication | Parent | Allows a new parent to self-register an account with full name, email and password before being linked to a student. | Trần Quốc Huy | Done | iter1 | none
3 | Logout | Authentication | Admin, Parent, Driver | Invalidates the current session and returns the user to the Login screen. | Trần Quốc Huy | Done | iter1 | none
4 | Forgot Password | Authentication | Admin, Parent, Driver | Allows a user to request a password reset email when the current password is forgotten. | Trần Quốc Huy | Done | iter1 | none
5 | Change Password | Authentication | Admin, Parent, Driver | Allows a logged-in user to change their current password after verifying the old one. | Trần Quốc Huy | Done | iter1 | none
6 | Google Login | Authentication | Parent | Allows a user to sign in using their Google account via OAuth callback. | Kiều Đình Đức | Done | iter2 | none
7 | Admin Dashboard | Dashboard | Admin | Displays overall statistics: total students, drivers, vehicles, routes, trips in progress and recent notifications. | Trần Quốc Huy | Done | iter2 | none
8 | Driver Dashboard | Dashboard | Driver | Displays the driver's assigned trips for the day and quick links to attendance and route. | Ngô Vương Tùng | Done | iter3 | none
9 | Parent Dashboard | Dashboard | Parent | Displays a summary of the parent's linked students, latest attendance and notifications. | Huỳnh Thị Thùy Trang | Done | iter3 | none
10 | Manage Classes | Class Management | Admin | Lists, searches, and manages academic classes that students are grouped into. | Kiều Đình Đức | Done | iter1 | none
11 | Add Class | Class Management | Admin | Allows the admin to create a new academic class with name, grade level, academic year and teacher. | Kiều Đình Đức | Done | iter1 | none
12 | Manage Parent Areas | Parent Area Management | Admin | Lists and manages geographical areas used to group parents, drivers and routes. | Kiều Đình Đức | Done | iter1 | none
13 | Manage Parents | Parent Management | Admin | Lists, searches and manages parent accounts and their information. | Kiều Đình Đức | Done | iter2 | none
14 | Add Parent | Parent Management | Admin | Allows the admin to create a new parent account and associated profile. | Kiều Đình Đức | Done | iter2 | none
15 | Update Parent | Parent Management | Admin | Allows the admin to edit an existing parent's profile information. | Kiều Đình Đức | Done | iter2 | none
16 | Link Parent to Student | Parent Management | Admin | Allows the admin to associate an existing parent account with one or more students. | Kiều Đình Đức | Done | iter2 | none
17 | Manage Drivers | Driver Management | Admin | Lists, searches and manages driver records including license and assigned vehicle. | Đào Hoàng Ân | Done | iter2 | none
18 | Add Driver | Driver Management | Admin | Allows the admin to create a new driver account with license number and area. | Đào Hoàng Ân | Done | iter2 | none
19 | Update Driver | Driver Management | Admin | Allows the admin to edit an existing driver's information. | Đào Hoàng Ân | Done | iter2 | none
20 | Delete Driver | Driver Management | Admin | Allows the admin to remove a driver record from the system. | Đào Hoàng Ân | Done | iter2 | none
21 | Manage Vehicles | Vehicle Management | Admin | Lists, searches and manages school bus (vehicle) records. | Đào Hoàng Ân | Done | iter2 | none
22 | Add Vehicle | Vehicle Management | Admin | Allows the admin to register a new vehicle with license plate, capacity and status. | Đào Hoàng Ân | Done | iter2 | none
23 | Update Vehicle | Vehicle Management | Admin | Allows the admin to edit an existing vehicle's information. | Đào Hoàng Ân | Done | iter2 | none
24 | Delete Vehicle | Vehicle Management | Admin | Allows the admin to remove a vehicle record from the system. | Đào Hoàng Ân | Done | iter2 | none
25 | Manage Routes | Route Management | Admin | Lists, searches and manages bus routes, including assigned driver and area. | Ngô Vương Tùng | Done | iter2 | none
26 | Add Route | Route Management | Admin | Allows the admin to create a new route with description, driver and area. | Ngô Vương Tùng | Done | iter2 | none
27 | Update Route | Route Management | Admin | Allows the admin to edit an existing route's information. | Ngô Vương Tùng | Done | iter2 | none
28 | Manage Students | Student Management | Admin | Lists, searches and manages student records, including class, parent and route assignment. | Huỳnh Thị Thùy Trang | Done | iter2 | none
29 | Add Student | Student Management | Admin | Allows the admin to add a new student and assign parent, class and route. | Huỳnh Thị Thùy Trang | Done | iter2 | none
30 | Update Student | Student Management | Admin | Allows the admin to edit an existing student's information. | Huỳnh Thị Thùy Trang | Done | iter2 | none
31 | Delete Student | Student Management | Admin | Allows the admin to remove a student record from the system. | Huỳnh Thị Thùy Trang | Done | iter2 | none
32 | Manage Trips (Admin) | Trip Management | Admin | Lists and monitors all scheduled and in-progress trips across routes. | Ngô Vương Tùng | Done | iter3 | none
33 | Trip Details (Driver) | Trip Management | Driver | Shows the driver the details of an assigned trip, including the student list. | Ngô Vương Tùng | Done | iter3 | none
34 | Start Trip | Trip Management | Driver | Allows the driver to mark an assigned trip as started, changing its status to In Progress. | Ngô Vương Tùng | Done | iter3 | none
35 | End Trip | Trip Management | Driver | Allows the driver to mark an in-progress trip as completed. | Ngô Vương Tùng | Done | iter3 | none
36 | Driver Route | Trip Management | Driver | Displays the driver's assigned route with the ordered list of stops. | Ngô Vương Tùng | Done | iter3 | none
37 | Manage Attendance (Admin) | Attendance Management | Admin | Allows the admin to search and review attendance records recorded by drivers. | Huỳnh Thị Thùy Trang | Done | iter3 | none
38 | Record Attendance (Driver) | Attendance Management | Driver | Allows the driver to check-in and check-out students during an active trip. | Huỳnh Thị Thùy Trang | Done | iter3 | none
39 | Student Tracking (Parent) | Tracking | Parent | Allows a parent to view the real-time status/location of the bus their child is assigned to. | Đào Hoàng Ân | Done | iter3 | none
40 | Submit Leave Request (Parent) | Leave Request Management | Parent | Allows a parent to submit an absence/leave request for a student on a given date. | Đào Hoàng Ân | Done | iter3 | none
41 | Manage Leave Requests (Admin) | Leave Request Management | Admin | Allows the admin to review, approve or reject leave requests submitted by parents. | Đào Hoàng Ân | Done | iter3 | none
42 | View Notifications (Driver) | Notification Management | Driver | Displays notifications relevant to the driver's assigned trips. | Trần Quốc Huy | Done | iter4 | none
43 | View Notifications (Parent) | Notification Management | Parent | Displays notifications relevant to the parent's linked students. | Trần Quốc Huy | Done | iter4 | none
44 | Manage Notifications (Admin) | Notification Management | Admin | Allows the admin to create and broadcast notifications to users. | Trần Quốc Huy | Done | iter4 | none
45 | Submit Feedback (Parent) | Feedback Management | Parent | Allows a parent to submit feedback or an inquiry to the school administration. | Kiều Đình Đức | Done | iter4 | none
46 | Manage Feedbacks (Admin) | Feedback Management | Admin | Allows the admin to view and respond to feedback submitted by parents. | Kiều Đình Đức | Done | iter4 | none
47 | Driver Profile | Profile Management | Driver | Allows the driver to view and update their own profile information. | Ngô Vương Tùng | Done | iter4 | none
48 | Parent Profile | Profile Management | Parent | Allows the parent to view and update their own profile information. | Huỳnh Thị Thùy Trang | Done | iter4 | none
49 | Reports & Statistics | Reporting | Admin | Allows the admin to generate attendance, route, driver and vehicle reports. | Đào Hoàng Ân | Done | iter4 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Login | Authentication | Allows a registered user to sign in with email and password; on success the system redirects to the role-specific dashboard. | Trần Quốc Huy | Done | II.2 | II.2
2 | Register | Authentication | Allows a new parent to self-register an account with full name, email and password before being linked to a student. | Trần Quốc Huy | Done | II.2 | II.2
3 | Logout | Authentication | Invalidates the current session and returns the user to the Login screen. | Trần Quốc Huy | Done | II.2 | II.2
4 | Forgot Password | Authentication | Allows a user to request a password reset email when the current password is forgotten. | Trần Quốc Huy | Done | II.2 | II.2
5 | Change Password | Authentication | Allows a logged-in user to change their current password after verifying the old one. | Trần Quốc Huy | Done | II.2 | II.2
6 | Manage Classes | Class Management | Lists, searches, and manages academic classes that students are grouped into. | Kiều Đình Đức | Done | II.3 | II.4
7 | Add Class | Class Management | Allows the admin to create a new academic class with name, grade level, academic year and teacher. | Kiều Đình Đức | Done | II.3 | II.4
8 | Manage Parent Areas | Parent Area Management | Lists and manages geographical areas used to group parents, drivers and routes. | Kiều Đình Đức | Done | II.3 | II.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Google Login | Authentication | Allows a user to sign in using their Google account via OAuth callback. | Kiều Đình Đức | Done | II.2 | II.2
2 | Admin Dashboard | Dashboard | Displays overall statistics: total students, drivers, vehicles, routes, trips in progress and recent notifications. | Trần Quốc Huy | Done | - | -
3 | Manage Parents | Parent Management | Lists, searches and manages parent accounts and their information. | Kiều Đình Đức | Done | II.3 | II.4
4 | Add Parent | Parent Management | Allows the admin to create a new parent account and associated profile. | Kiều Đình Đức | Done | II.3 | II.4
5 | Update Parent | Parent Management | Allows the admin to edit an existing parent's profile information. | Kiều Đình Đức | Done | II.3 | II.4
6 | Link Parent to Student | Parent Management | Allows the admin to associate an existing parent account with one or more students. | Kiều Đình Đức | Done | II.3 | II.4
7 | Manage Drivers | Driver Management | Lists, searches and manages driver records including license and assigned vehicle. | Đào Hoàng Ân | Done | II.3 | II.4
8 | Add Driver | Driver Management | Allows the admin to create a new driver account with license number and area. | Đào Hoàng Ân | Done | II.3 | II.4
9 | Update Driver | Driver Management | Allows the admin to edit an existing driver's information. | Đào Hoàng Ân | Done | II.3 | II.4
10 | Delete Driver | Driver Management | Allows the admin to remove a driver record from the system. | Đào Hoàng Ân | Done | II.3 | II.4
11 | Manage Vehicles | Vehicle Management | Lists, searches and manages school bus (vehicle) records. | Đào Hoàng Ân | Done | II.3 | II.4
12 | Add Vehicle | Vehicle Management | Allows the admin to register a new vehicle with license plate, capacity and status. | Đào Hoàng Ân | Done | II.3 | II.4
13 | Update Vehicle | Vehicle Management | Allows the admin to edit an existing vehicle's information. | Đào Hoàng Ân | Done | II.3 | II.4
14 | Delete Vehicle | Vehicle Management | Allows the admin to remove a vehicle record from the system. | Đào Hoàng Ân | Done | II.3 | II.4
15 | Manage Routes | Route Management | Lists, searches and manages bus routes, including assigned driver and area. | Ngô Vương Tùng | Done | II.3 | II.4
16 | Add Route | Route Management | Allows the admin to create a new route with description, driver and area. | Ngô Vương Tùng | Done | II.3 | II.4
17 | Update Route | Route Management | Allows the admin to edit an existing route's information. | Ngô Vương Tùng | Done | II.3 | II.4
18 | Manage Students | Student Management | Lists, searches and manages student records, including class, parent and route assignment. | Huỳnh Thị Thùy Trang | Done | II.1 | II.1
19 | Add Student | Student Management | Allows the admin to add a new student and assign parent, class and route. | Huỳnh Thị Thùy Trang | Done | II.1 | II.1
20 | Update Student | Student Management | Allows the admin to edit an existing student's information. | Huỳnh Thị Thùy Trang | Done | II.1 | II.1
21 | Delete Student | Student Management | Allows the admin to remove a student record from the system. | Huỳnh Thị Thùy Trang | Done | II.1 | II.1
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Driver Dashboard | Dashboard | Displays the driver's assigned trips for the day and quick links to attendance and route. | Ngô Vương Tùng | Done | - | -
2 | Parent Dashboard | Dashboard | Displays a summary of the parent's linked students, latest attendance and notifications. | Huỳnh Thị Thùy Trang | Done | - | -
3 | Manage Trips (Admin) | Trip Management | Lists and monitors all scheduled and in-progress trips across routes. | Ngô Vương Tùng | Done | II.4 | II.3
4 | Trip Details (Driver) | Trip Management | Shows the driver the details of an assigned trip, including the student list. | Ngô Vương Tùng | Done | II.4 | II.3
5 | Start Trip | Trip Management | Allows the driver to mark an assigned trip as started, changing its status to In Progress. | Ngô Vương Tùng | Done | II.4 | II.3
6 | End Trip | Trip Management | Allows the driver to mark an in-progress trip as completed. | Ngô Vương Tùng | Done | II.4 | II.3
7 | Driver Route | Trip Management | Displays the driver's assigned route with the ordered list of stops. | Ngô Vương Tùng | Done | II.4 | II.3
8 | Manage Attendance (Admin) | Attendance Management | Allows the admin to search and review attendance records recorded by drivers. | Huỳnh Thị Thùy Trang | Done | II.4 | II.3
9 | Record Attendance (Driver) | Attendance Management | Allows the driver to check-in and check-out students during an active trip. | Huỳnh Thị Thùy Trang | Done | II.4 | II.3
10 | Student Tracking (Parent) | Tracking | Allows a parent to view the real-time status/location of the bus their child is assigned to. | Đào Hoàng Ân | Done | II.5 | -
11 | Submit Leave Request (Parent) | Leave Request Management | Allows a parent to submit an absence/leave request for a student on a given date. | Đào Hoàng Ân | Done | II.5 | -
12 | Manage Leave Requests (Admin) | Leave Request Management | Allows the admin to review, approve or reject leave requests submitted by parents. | Đào Hoàng Ân | Done | II.5 | -
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | View Notifications (Driver) | Notification Management | Displays notifications relevant to the driver's assigned trips. | Trần Quốc Huy | Done | II.5 | -
2 | View Notifications (Parent) | Notification Management | Displays notifications relevant to the parent's linked students. | Trần Quốc Huy | Done | II.5 | -
3 | Manage Notifications (Admin) | Notification Management | Allows the admin to create and broadcast notifications to users. | Trần Quốc Huy | Done | II.5 | -
4 | Submit Feedback (Parent) | Feedback Management | Allows a parent to submit feedback or an inquiry to the school administration. | Kiều Đình Đức | Done | II.5 | -
5 | Manage Feedbacks (Admin) | Feedback Management | Allows the admin to view and respond to feedback submitted by parents. | Kiều Đình Đức | Done | II.5 | -
6 | Driver Profile | Profile Management | Allows the driver to view and update their own profile information. | Ngô Vương Tùng | Done | - | -
7 | Parent Profile | Profile Management | Allows the parent to view and update their own profile information. | Huỳnh Thị Thùy Trang | Done | - | -
8 | Reports & Statistics | Reporting | Allows the admin to generate attendance, route, driver and vehicle reports. | Đào Hoàng Ân | Done | - | -
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document