## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Implement Login | Develop and unit test the Login function/screen for actor(s): Admin, Parent, Driver. Allows a registered user to sign in with email and password; on success the system redirects to the role-specific dashboard. | 1 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/1 | Closed | HuyTQ | 2026-05-04 09:00 | 2026-05-10 09:00 | iter1 | Task, 3_Done | Login
Implement Register | Develop and unit test the Register function/screen for actor(s): Parent. Allows a new parent to self-register an account with full name, email and password before being linked to a student. | 2 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/2 | Closed | HuyTQ | 2026-05-04 09:00 | 2026-05-10 09:00 | iter1 | Task, 3_Done | Register
Implement Logout | Develop and unit test the Logout function/screen for actor(s): Admin, Parent, Driver. Invalidates the current session and returns the user to the Login screen. | 3 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/3 | Closed | HuyTQ | 2026-05-04 09:00 | 2026-05-10 09:00 | iter1 | Task, 3_Done | Logout
Implement Forgot Password | Develop and unit test the Forgot Password function/screen for actor(s): Admin, Parent, Driver. Allows a user to request a password reset email when the current password is forgotten. | 4 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/4 | Closed | HuyTQ | 2026-05-04 09:00 | 2026-05-10 09:00 | iter1 | Task, 3_Done | Forgot Password
Implement Change Password | Develop and unit test the Change Password function/screen for actor(s): Admin, Parent, Driver. Allows a logged-in user to change their current password after verifying the old one. | 5 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/5 | Closed | HuyTQ | 2026-05-04 09:00 | 2026-05-10 09:00 | iter1 | Task, 3_Done | Change Password
Implement Google Login | Develop and unit test the Google Login function/screen for actor(s): Parent. Allows a user to sign in using their Google account via OAuth callback. | 6 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/6 | Closed | DucKD | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Google Login
Implement Admin Dashboard | Develop and unit test the Admin Dashboard function/screen for actor(s): Admin. Displays overall statistics: total students, drivers, vehicles, routes, trips in progress and recent notifications. | 7 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/7 | Closed | HuyTQ | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Admin Dashboard
Implement Driver Dashboard | Develop and unit test the Driver Dashboard function/screen for actor(s): Driver. Displays the driver's assigned trips for the day and quick links to attendance and route. | 8 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/8 | Closed | TungNV | 2026-05-24 09:00 | 2026-05-30 09:00 | iter3 | Task, 3_Done | Driver Dashboard
Implement Parent Dashboard | Develop and unit test the Parent Dashboard function/screen for actor(s): Parent. Displays a summary of the parent's linked students, latest attendance and notifications. | 9 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/9 | Closed | TrangHTT | 2026-05-24 09:00 | 2026-05-30 09:00 | iter3 | Task, 3_Done | Parent Dashboard
Implement Manage Classes | Develop and unit test the Manage Classes function/screen for actor(s): Admin. Lists, searches, and manages academic classes that students are grouped into. | 10 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/10 | Closed | DucKD | 2026-05-04 09:00 | 2026-05-10 09:00 | iter1 | Task, 3_Done | Manage Classes
Implement Add Class | Develop and unit test the Add Class function/screen for actor(s): Admin. Allows the admin to create a new academic class with name, grade level, academic year and teacher. | 11 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/11 | Closed | DucKD | 2026-05-04 09:00 | 2026-05-10 09:00 | iter1 | Task, 3_Done | Add Class
Implement Manage Parent Areas | Develop and unit test the Manage Parent Areas function/screen for actor(s): Admin. Lists and manages geographical areas used to group parents, drivers and routes. | 12 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/12 | Closed | DucKD | 2026-05-04 09:00 | 2026-05-10 09:00 | iter1 | Task, 3_Done | Manage Parent Areas
Implement Manage Parents | Develop and unit test the Manage Parents function/screen for actor(s): Admin. Lists, searches and manages parent accounts and their information. | 13 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/13 | Closed | DucKD | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Manage Parents
Implement Add Parent | Develop and unit test the Add Parent function/screen for actor(s): Admin. Allows the admin to create a new parent account and associated profile. | 14 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/14 | Closed | DucKD | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Add Parent
Implement Update Parent | Develop and unit test the Update Parent function/screen for actor(s): Admin. Allows the admin to edit an existing parent's profile information. | 15 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/15 | Closed | DucKD | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Update Parent
Implement Link Parent to Student | Develop and unit test the Link Parent to Student function/screen for actor(s): Admin. Allows the admin to associate an existing parent account with one or more students. | 16 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/16 | Closed | DucKD | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Link Parent to Student
Implement Manage Drivers | Develop and unit test the Manage Drivers function/screen for actor(s): Admin. Lists, searches and manages driver records including license and assigned vehicle. | 17 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/17 | Closed | AnDH | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Manage Drivers
Implement Add Driver | Develop and unit test the Add Driver function/screen for actor(s): Admin. Allows the admin to create a new driver account with license number and area. | 18 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/18 | Closed | AnDH | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Add Driver
Implement Update Driver | Develop and unit test the Update Driver function/screen for actor(s): Admin. Allows the admin to edit an existing driver's information. | 19 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/19 | Closed | AnDH | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Update Driver
Implement Delete Driver | Develop and unit test the Delete Driver function/screen for actor(s): Admin. Allows the admin to remove a driver record from the system. | 20 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/20 | Closed | AnDH | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Delete Driver
Implement Manage Vehicles | Develop and unit test the Manage Vehicles function/screen for actor(s): Admin. Lists, searches and manages school bus (vehicle) records. | 21 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/21 | Closed | AnDH | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Manage Vehicles
Implement Add Vehicle | Develop and unit test the Add Vehicle function/screen for actor(s): Admin. Allows the admin to register a new vehicle with license plate, capacity and status. | 22 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/22 | Closed | AnDH | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Add Vehicle
Implement Update Vehicle | Develop and unit test the Update Vehicle function/screen for actor(s): Admin. Allows the admin to edit an existing vehicle's information. | 23 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/23 | Closed | AnDH | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Update Vehicle
Implement Delete Vehicle | Develop and unit test the Delete Vehicle function/screen for actor(s): Admin. Allows the admin to remove a vehicle record from the system. | 24 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/24 | Closed | AnDH | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Delete Vehicle
Implement Manage Routes | Develop and unit test the Manage Routes function/screen for actor(s): Admin. Lists, searches and manages bus routes, including assigned driver and area. | 25 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/25 | Closed | TungNV | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Manage Routes
Implement Add Route | Develop and unit test the Add Route function/screen for actor(s): Admin. Allows the admin to create a new route with description, driver and area. | 26 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/26 | Closed | TungNV | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Add Route
Implement Update Route | Develop and unit test the Update Route function/screen for actor(s): Admin. Allows the admin to edit an existing route's information. | 27 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/27 | Closed | TungNV | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Update Route
Implement Manage Students | Develop and unit test the Manage Students function/screen for actor(s): Admin. Lists, searches and manages student records, including class, parent and route assignment. | 28 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/28 | Closed | TrangHTT | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Manage Students
Implement Add Student | Develop and unit test the Add Student function/screen for actor(s): Admin. Allows the admin to add a new student and assign parent, class and route. | 29 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/29 | Closed | TrangHTT | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Add Student
Implement Update Student | Develop and unit test the Update Student function/screen for actor(s): Admin. Allows the admin to edit an existing student's information. | 30 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/30 | Closed | TrangHTT | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Update Student
Implement Delete Student | Develop and unit test the Delete Student function/screen for actor(s): Admin. Allows the admin to remove a student record from the system. | 31 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/31 | Closed | TrangHTT | 2026-05-14 09:00 | 2026-05-20 09:00 | iter2 | Task, 3_Done | Delete Student
Implement Manage Trips (Admin) | Develop and unit test the Manage Trips (Admin) function/screen for actor(s): Admin. Lists and monitors all scheduled and in-progress trips across routes. | 32 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/32 | Closed | TungNV | 2026-05-24 09:00 | 2026-05-30 09:00 | iter3 | Task, 3_Done | Manage Trips (Admin)
Implement Trip Details (Driver) | Develop and unit test the Trip Details (Driver) function/screen for actor(s): Driver. Shows the driver the details of an assigned trip, including the student list. | 33 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/33 | Closed | TungNV | 2026-05-24 09:00 | 2026-05-30 09:00 | iter3 | Task, 3_Done | Trip Details (Driver)
Implement Start Trip | Develop and unit test the Start Trip function/screen for actor(s): Driver. Allows the driver to mark an assigned trip as started, changing its status to In Progress. | 34 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/34 | Closed | TungNV | 2026-05-24 09:00 | 2026-05-30 09:00 | iter3 | Task, 3_Done | Start Trip
Implement End Trip | Develop and unit test the End Trip function/screen for actor(s): Driver. Allows the driver to mark an in-progress trip as completed. | 35 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/35 | Closed | TungNV | 2026-05-24 09:00 | 2026-05-30 09:00 | iter3 | Task, 3_Done | End Trip
Implement Driver Route | Develop and unit test the Driver Route function/screen for actor(s): Driver. Displays the driver's assigned route with the ordered list of stops. | 36 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/36 | Closed | TungNV | 2026-05-24 09:00 | 2026-05-30 09:00 | iter3 | Task, 3_Done | Driver Route
Implement Manage Attendance (Admin) | Develop and unit test the Manage Attendance (Admin) function/screen for actor(s): Admin. Allows the admin to search and review attendance records recorded by drivers. | 37 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/37 | Closed | TrangHTT | 2026-05-24 09:00 | 2026-05-30 09:00 | iter3 | Task, 3_Done | Manage Attendance (Admin)
Implement Record Attendance (Driver) | Develop and unit test the Record Attendance (Driver) function/screen for actor(s): Driver. Allows the driver to check-in and check-out students during an active trip. | 38 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/38 | Closed | TrangHTT | 2026-05-24 09:00 | 2026-05-30 09:00 | iter3 | Task, 3_Done | Record Attendance (Driver)
Implement Student Tracking (Parent) | Develop and unit test the Student Tracking (Parent) function/screen for actor(s): Parent. Allows a parent to view the real-time status/location of the bus their child is assigned to. | 39 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/39 | Closed | AnDH | 2026-05-24 09:00 | 2026-05-30 09:00 | iter3 | Task, 3_Done | Student Tracking (Parent)
Implement Submit Leave Request (Parent) | Develop and unit test the Submit Leave Request (Parent) function/screen for actor(s): Parent. Allows a parent to submit an absence/leave request for a student on a given date. | 40 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/40 | Closed | AnDH | 2026-05-24 09:00 | 2026-05-30 09:00 | iter3 | Task, 3_Done | Submit Leave Request (Parent)
Implement Manage Leave Requests (Admin) | Develop and unit test the Manage Leave Requests (Admin) function/screen for actor(s): Admin. Allows the admin to review, approve or reject leave requests submitted by parents. | 41 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/41 | Closed | AnDH | 2026-05-24 09:00 | 2026-05-30 09:00 | iter3 | Task, 3_Done | Manage Leave Requests (Admin)
Implement View Notifications (Driver) | Develop and unit test the View Notifications (Driver) function/screen for actor(s): Driver. Displays notifications relevant to the driver's assigned trips. | 42 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/42 | Closed | HuyTQ | 2026-06-03 09:00 | 2026-06-09 09:00 | iter4 | Task, 3_Done | View Notifications (Driver)
Implement View Notifications (Parent) | Develop and unit test the View Notifications (Parent) function/screen for actor(s): Parent. Displays notifications relevant to the parent's linked students. | 43 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/43 | Closed | HuyTQ | 2026-06-03 09:00 | 2026-06-09 09:00 | iter4 | Task, 3_Done | View Notifications (Parent)
Implement Manage Notifications (Admin) | Develop and unit test the Manage Notifications (Admin) function/screen for actor(s): Admin. Allows the admin to create and broadcast notifications to users. | 44 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/44 | Closed | HuyTQ | 2026-06-03 09:00 | 2026-06-09 09:00 | iter4 | Task, 3_Done | Manage Notifications (Admin)
Implement Submit Feedback (Parent) | Develop and unit test the Submit Feedback (Parent) function/screen for actor(s): Parent. Allows a parent to submit feedback or an inquiry to the school administration. | 45 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/45 | Closed | DucKD | 2026-06-03 09:00 | 2026-06-09 09:00 | iter4 | Task, 3_Done | Submit Feedback (Parent)
Implement Manage Feedbacks (Admin) | Develop and unit test the Manage Feedbacks (Admin) function/screen for actor(s): Admin. Allows the admin to view and respond to feedback submitted by parents. | 46 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/46 | Closed | DucKD | 2026-06-03 09:00 | 2026-06-09 09:00 | iter4 | Task, 3_Done | Manage Feedbacks (Admin)
Implement Driver Profile | Develop and unit test the Driver Profile function/screen for actor(s): Driver. Allows the driver to view and update their own profile information. | 47 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/47 | Closed | TungNV | 2026-06-03 09:00 | 2026-06-09 09:00 | iter4 | Task, 3_Done | Driver Profile
Implement Parent Profile | Develop and unit test the Parent Profile function/screen for actor(s): Parent. Allows the parent to view and update their own profile information. | 48 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/48 | Closed | TrangHTT | 2026-06-03 09:00 | 2026-06-09 09:00 | iter4 | Task, 3_Done | Parent Profile
Implement Reports & Statistics | Develop and unit test the Reports & Statistics function/screen for actor(s): Admin. Allows the admin to generate attendance, route, driver and vehicle reports. | 49 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/49 | Closed | AnDH | 2026-06-03 09:00 | 2026-06-09 09:00 | iter4 | Task, 3_Done | Reports & Statistics
Login accepts inactive account | During EP/BVA testing, an account with status=0 (disabled) could still authenticate via /auth/login. | 50 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/50 | Closed | DucKD | 2026-05-07 09:00 | 2026-05-09 09:00 | iter1 | Defect, 3_Done | Login
Attendance checkout allowed before checkin | Decision Table testing found that checkout could be recorded for a student who had not been checked in on the trip. | 51 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/51 | Closed | TrangHTT | 2026-05-27 09:00 | 2026-05-29 09:00 | iter3 | Defect, 3_Done | Record Attendance (Driver)
Duplicate license plate not rejected on Add Vehicle | Boundary testing showed the Add Vehicle form allowed saving a vehicle with a license plate already in use. | 52 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/52 | Closed | AnDH | 2026-05-17 09:00 | 2026-05-19 09:00 | iter2 | Defect, 3_Done | Add Vehicle
Leave request date allowed in the past | Leave Request form did not validate that leave_date must be today or later. | 53 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/53 | Closed | AnDH | 2026-05-27 09:00 | 2026-05-29 09:00 | iter3 | Defect, 3_Done | Submit Leave Request (Parent)
Route Servlet redirect assertion failing in Postman | pm.response.url returned empty after 302 redirect in Collection Runner; assertions rewritten to use status code and response time instead of URL matching. | 54 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/54 | Closed | HuyTQ | 2026-05-27 09:00 | 2026-05-29 09:00 | iter3 | Defect, 3_Done | Driver Route
H2 BIT column mismatch in integration tests | H2 treats BIT as strict BOOLEAN causing DAO integration tests to fail; fixed by using TINYINT in the H2 test schema. | 55 | https://github.com/fudn-traltb-su26/rbl-swt301-theo-tu-n-groupname-strong/issues/55 | Closed | HuyTQ | 2026-05-17 09:00 | 2026-05-19 09:00 | iter2 | Defect, 3_Done | Manage Students